PRIMAVERA P6 RESEARCH DOCUMENT

For SiteSync — Smart India Hackathon 2026

Understanding Primavera, WBS Levels (L1–L6), Scheduling Data, Export Formats and Integration with SiteSync

Team: CoDelulu

Research basis: Oracle Primavera P6 / Primavera Cloud official documentation, supplemented with project-specific interpretation for the SiteSync SIH solution.

# 1. Executive Summary

Oracle Primavera P6 is a professional project planning and scheduling platform widely used for complex engineering, construction and infrastructure projects. It represents the planned project using projects, WBS structures, activities, activity relationships, calendars, resources, costs, baselines and progress/status information.

For the SiteSync SIH solution, Primavera should be viewed as the source of the planned schedule: it tells the organization what work is planned, how activities depend on one another, and what dates and durations are expected. SiteSync is intended to capture actual field progress, especially under poor connectivity, and connect those observations back to the planned schedule.

The most important integration concept is therefore:

PRIMAVERA P6 (PLAN) → Export/Integration → SITESYNC → Actual Field Progress → Plan vs Actual → DAG/CPM → Delay/Critical-Path Impact → Dashboard

A critical clarification: L1, L2, L3, L4, L5 and L6 are not six fixed Primavera categories. They normally refer to levels in a project's Work Breakdown Structure (WBS), but the meaning assigned to each level is decided by the organization/project. Primavera supports hierarchical WBS structures; teams may choose to use six levels, fewer, or more.

# 2. What is Primavera P6?

Primavera P6 is Oracle's project planning and scheduling software. It is designed to model large projects with many activities, dependencies, calendars, resources, costs and progress updates.

In simple terms, Primavera answers questions such as:

• What work has to be done?

• How is the work divided into manageable packages?

• When should each activity start and finish?

• Which activity must happen before another activity?

• Which activities are critical to the project completion date?

• How much work has actually been completed?

• How far is the current schedule from the approved baseline?

• What happens to downstream work if an activity is delayed?

For SiteSync, the important distinction is between planned information and actual information. Primavera contains the planned schedule and can also contain schedule updates; SiteSync focuses on making actual field capture fast, offline-capable and easy to synchronize.

# 3. Primavera P6 Product Names: P6 Professional, P6 EPPM and Primavera Cloud

The word 'Primavera' is often used loosely. For integration discussions, distinguish the products/environments.

| Product / Environment | Simple description | Why it matters to SiteSync |
| --- | --- | --- |
| P6 Professional | Desktop-oriented P6 application used for detailed project planning and scheduling. | A common source of XER/XML project files and spreadsheet exports. |
| P6 EPPM | Enterprise/project-management environment with web and integration capabilities. | Relevant when the organization exposes enterprise data or APIs. |
| Primavera Cloud | Oracle cloud platform that can exchange project data with P6 using P6 XML/XER. | Relevant if the organization is using Oracle's cloud environment and API-based integration. |

# 4. Project Hierarchy: EPS, Project, WBS and Activities

It is useful to think of Primavera as several layers of organization rather than one flat task list.

Enterprise / Company
    ↓
EPS (Enterprise Project Structure)
    ↓
Project
    ↓
WBS (Work Breakdown Structure)
    ↓
Activities

## 4.1 EPS — Enterprise Project Structure

EPS is the organizational hierarchy used to arrange projects. A company may group projects under business units, divisions, regions or other organizational structures. EPS is therefore about organizing projects at the enterprise level.

## 4.2 Project

A project is the individual scheduled effort being planned and controlled, such as a pipeline construction project, highway project, refinery project or building project.

## 4.3 WBS — Work Breakdown Structure

WBS is the hierarchical breakdown of the work/scope inside a project. A WBS node can contain lower-level WBS nodes and/or activities. It provides structure for grouping, summarizing and managing the schedule.

## 4.4 Activity

An activity is an actual scheduled piece of work or a milestone in the project. Activities have identifiers, names, dates, durations, status/progress information and relationships with other activities.

# 5. Understanding L1, L2, L3, L4, L5 and L6

This is the section most likely to cause confusion. L1–L6 normally means hierarchy levels within a WBS or another project breakdown convention. There is no universal Oracle rule that says 'L1 is always Project, L2 is always Area, L3 is always System, ...'. The project organization decides what each level represents.

Oracle's documentation describes WBS as a hierarchical arrangement of work and notes that WBS levels can be displayed/grouped hierarchically. In Primavera Cloud, WBS codes are hierarchical and child nodes can be created beneath parent nodes.

## 5.1 Example of a Six-Level WBS for an Oil & Gas Pipeline Project

| Level | Example label | Possible meaning |
| --- | --- | --- |
| L1 | Pipeline Construction Project | Entire project / top-level WBS |
| L2 | Section A | Major geographic or project section |
| L3 | Pipeline Installation | Major work package / discipline |
| L4 | Welding | Specific construction activity group |
| L5 | Chainage 10–20 km | Location / sub-package |
| L6 | Weld Joint 1042 | Very detailed work package or execution grouping |

Important: the table above is an example for understanding the concept. It is not a mandatory Primavera hierarchy. A different contractor might define L1–L6 completely differently.

## 5.2 Another Common Style of Six-Level Hierarchy

| Level | Possible organization-specific meaning |
| --- | --- |
| L1 | Project |
| L2 | Area / Location |
| L3 | System |
| L4 | Subsystem / Discipline |
| L5 | Work Package |
| L6 | Detailed Work Package / Activity grouping |

The key principle is that each level becomes more specific. When building SiteSync, the software should not hard-code assumptions such as 'L4 always means Welding'. Instead, the imported WBS hierarchy should be read from the Primavera project itself.

# 6. WBS Code vs WBS Level vs Activity ID

These three concepts should not be mixed up.

| Term | Meaning | Example |
| --- | --- | --- |
| WBS level | Position/depth in the hierarchy. | L4 |
| WBS code | Identifier representing a WBS node. | 1.2.3.4 |
| WBS name | Human-readable name of the WBS node. | Pipeline Welding |
| Activity ID | Unique identifier of a scheduled activity. | WELD-1042 |
| Activity name | Human-readable activity description. | Weld Joint 1042 |

For SiteSync, the Activity ID is especially important because a field update should ultimately be linked to a specific scheduled activity. WBS information is then used to provide context, filtering and roll-up.

# 7. WBS and Activities: A Concrete Example

Project: Pipeline Construction
└── WBS L2: Section A
    └── WBS L3: Pipeline Installation
        ├── WBS L4: Stringing
        │   ├── Activity: STR-001
        │   └── Activity: STR-002
        ├── WBS L4: Welding
        │   ├── Activity: WELD-001
        │   └── Activity: WELD-002
        └── WBS L4: NDT
            ├── Activity: NDT-001
            └── Activity: NDT-002

In this example, 'Welding' is a WBS grouping while WELD-001 and WELD-002 are actual scheduled activities. A worker's report should normally be associated with the activity, not merely with the WBS label.

# 8. Activity Data in Primavera

An activity can contain many attributes. For SiteSync, the most important categories are identity, hierarchy, schedule dates, progress, relationships and optional resources/costs.

| Category | Important fields / concepts | Why SiteSync may need it |
| --- | --- | --- |
| Identity | Project ID, Activity ID, Activity Name | Match a field update to the correct scheduled activity. |
| Hierarchy | WBS Code, WBS Name | Understand where the activity belongs in the project. |
| Dates | Planned/early/actual start and finish dates | Compare plan vs actual. |
| Duration | Original/planned/remaining duration | Measure schedule progress and variance. |
| Progress | Activity %, Physical %, Duration %, Units % | Represent actual progress correctly. |
| Relationships | Predecessor, Successor, Type, Lag | Build the dependency graph. |
| Constraints | Start/finish constraints | Avoid incorrectly moving activities. |
| Calendar | Working/non-working periods | Interpret dates and durations correctly. |
| Baseline | Baseline dates/values | Compare current plan against approved plan. |
| Resources | Labor/nonlabor resources and assignments | Optional workforce/equipment intelligence. |
| Costs | Planned, actual and remaining costs | Optional cost-impact analysis. |

# 9. Activity Relationships

Relationships define the logical dependency between activities. Oracle documents four relationship types.

| Type | Meaning | Example |
| --- | --- | --- |
| FS — Finish to Start | Successor starts after predecessor finishes. | Welding finishes → NDT starts. |
| SS — Start to Start | Successor start depends on predecessor start. | Excavation starts → related preparation can start. |
| FF — Finish to Finish | Successor finish depends on predecessor finish. | Two coordinated work packages finish together. |
| SF — Start to Finish | Successor cannot finish until predecessor starts. | Rare; used in specialized scheduling situations. |

Finish-to-Start is the default/common relationship type. Relationships can also have lag. Positive lag adds waiting time; negative lag (lead) can allow a successor to begin before the predecessor's related start/finish point.

For SiteSync, relationships are crucial because they become the edges of the schedule graph. Activities are the nodes; relationships are the directed edges.

# 10. How Primavera Becomes a DAG for SiteSync

Activity A: Stringing
        │
        │ FS
        ▼
Activity B: Welding
        │
        │ FS
        ▼
Activity C: NDT
        │
        │ FS
        ▼
Activity D: Lowering

This is conceptually a Directed Acyclic Graph (DAG): each activity is a node and each dependency is a directed edge. SiteSync can ingest Primavera activities and relationships, then construct its internal graph for critical-path and downstream-impact analysis.

Caution: a real Primavera schedule may contain multiple relationship types, lag, constraints, calendars and cross-project relationships. The SiteSync graph layer must preserve enough information to reproduce the schedule logic accurately rather than reducing every relationship to a simple arrow.

# 11. Progress and Percent Complete

One of the most important details for SiteSync is that 'percent complete' is not necessarily one universal number in P6. The meaning depends on the activity's Percent Complete Type.

| Percent Complete Type | How it works | Typical use |
| --- | --- | --- |
| Duration | Calculated from original/planned duration and remaining duration. | Duration-driven work such as training or administrative tasks. |
| Units | Calculated from actual and remaining labor/nonlabor units. | Work-effort-driven activities. |
| Physical | Entered by the user or calculated from activity steps. | Work-product-driven construction activities. |
| Scope | Calculated by Oracle Primavera Cloud; not editable in P6 for this use case. | Scope-management integration scenarios. |

For construction and infrastructure, Physical % Complete can be especially relevant because a worker may know that a physical work product is 70% complete even when elapsed time or labor units do not indicate 70%.

SiteSync should therefore avoid blindly interpreting every field update such as '70% complete' as one generic metric. The target activity's percent-complete configuration should be considered.

# 12. Planned vs Actual: The Data SiteSync Needs

| Dimension | Planned | Actual / Field Update |
| --- | --- | --- |
| Start | Planned/baseline start | Actual start |
| Finish | Planned/baseline finish | Actual finish or forecast finish |
| Duration | Original/planned duration | Actual/remaining duration |
| Progress | Expected progress by data date | Reported/physical progress |
| Status | Planned/not started | Started / in progress / completed |
| Issue | Not necessarily present | Delay reason, obstruction, equipment issue, etc. |
| Dependency impact | Existing relationship logic | Recalculated effect after actual update |

The Data Date is important. In P6 Professional, the Data Date is the date used as the starting point to calculate the schedule. A SiteSync integration should preserve the relationship between the field update timestamp, the reporting/data date and the schedule version being evaluated.

# 13. Baseline

A baseline is a saved reference plan against which current performance can be compared. In practical terms, it answers: 'What did we originally approve or commit to?'

Baseline Plan
     ↓
Current Schedule
     ↓
Actual Field Progress
     ↓
Variance / Impact

For SiteSync, baselines are useful because current planned dates can change during schedule updates. Comparing only against the latest plan may hide the fact that the project has already moved away from its original commitment. A baseline gives a stable reference.

# 14. Critical Path and Float

The critical path is the chain of schedule logic that controls the project completion date. P6 also exposes total float and longest-path concepts. An activity with zero float generally has little/no schedule flexibility, while negative float can indicate a schedule problem; however, the exact interpretation depends on the schedule configuration and network.

For SiteSync, the useful chain is:

Field delay → Activity status changes → Schedule recalculation → Float / longest-path impact → Downstream impact → Project finish risk

The SiteSync PPT proposes using DAG logic and Critical Path Method analysis to identify whether a field delay is merely local or whether it threatens the project completion date.

# 15. Primavera Data Export — Overview

Primavera can export project information in multiple formats. The most important formats for SiteSync integration are XER, P6 XML and Excel (XLS/XLSX). P6 also supports other formats for specific use cases.

| Format | What it is | SiteSync relevance |
| --- | --- | --- |
| XER | Oracle Primavera proprietary exchange format. | Very important for full P6 project exchange and backup/import workflows. |
| P6 XML | Structured XML representation of P6 project data. | Very useful for machine-readable integration and parsing. |
| XLS/XLSX | Spreadsheet exports of selected information such as activities and relationships. | Excellent for prototype/demo ingestion and human inspection. |
| Microsoft Project formats | Formats intended for Microsoft Project exchange. | Less suitable as the primary SiteSync source if Primavera is the source system. |
| UN/CEFACT XML | XML format for Integrated Master Schedule use cases. | Specialized; not the first choice for a SiteSync prototype. |
| IPMDAR / CPP JSON exports | Specialized collections of JSON files for certain reporting/use cases. | Potentially useful for specific enterprise reporting, but not the primary P6 schedule exchange path. |

Oracle's P6 Professional documentation states that XER can export complete project information for exchange with other P6 users, while P6 XML can export project/baseline information. Spreadsheet exports can separately provide activities, activity relationships, resources, resource assignments and expenses. Not every format contains the complete project information.

# 16. XER — Primavera Proprietary Exchange Format

XER is Oracle Primavera's proprietary exchange format. It is designed to exchange Primavera project information between P6 systems and is also useful as a project backup/export artifact.

## 16.1 Typical P6 Professional XER export flow

1. Open the required project(s) in P6 Professional.

2. Choose File → Export.

3. Select Primavera PM – (XER).

4. Select the appropriate XER version.

5. Choose the project(s) to export.

6. Specify the output file name/location.

7. Finish the export.

Oracle also documents scheduled/job-service export options when P6 Professional is connected to a P6 Professional database, and command-line service options for some environments.

## 16.2 What XER contains

An XER export is not simply a flat activity spreadsheet. Oracle's XER data map documents project-related entities including activities, activity relationships, activity steps, activity resource assignments, WBS information, calendars, codes, user-defined fields and other project objects.

For example, Oracle's XER data map identifies TASK as the activity data structure and TASKPRED as the activity relationship data structure. TASKPRED includes predecessor project/activity, successor project/activity, relationship type and lag.

## 16.3 Important XER relationship fields

| XER relationship field | Meaning |
| --- | --- |
| pred_proj_id | Predecessor project |
| pred_task_id | Predecessor activity |
| pred_type | Relationship type |
| proj_id | Successor project |
| task_id | Successor activity |
| lag_hr_cnt | Lag in hours |
| task_pred_id | Unique relationship ID |

These fields are especially valuable for SiteSync because they are enough to reconstruct the directed dependency edges needed by the DAG layer, provided the corresponding activity records are also imported.

# 17. P6 XML

P6 XML is a structured XML exchange format for Primavera project information. It is often easier for a software team to inspect and parse than a proprietary tabular exchange format because the data is represented as hierarchical XML elements.

At a conceptual level, an XML export can represent project information, WBS, activities, relationships, resources, calendars, baselines and related objects depending on what is exported and supported by the specific P6 product/version.

<Project>
  <WBS>...</WBS>
  <Activity>...</Activity>
  <Relationship>...</Relationship>
</Project>

The example above is illustrative rather than a literal dump of a specific P6 XML file. The exact XML schema and elements depend on the P6 product/version and export context.

# 18. Excel / XLSX Export

P6 Professional provides an Export Wizard for spreadsheet-based exports. Oracle documents XLSX exports for Activities, Activity Relationships, Expenses, Resources and Resource Assignments.

For a hackathon prototype, Excel can be an excellent starting point because the team can inspect the exported data manually, validate mappings and then build the parser/ingestion pipeline.

| Excel export | What the team can obtain | Prototype value |
| --- | --- | --- |
| Activities | Activity IDs, names and selected activity fields | Build the activity list and map field updates. |
| Activity Relationships | Predecessor/successor IDs and relationship information | Build DAG edges. |
| Resources | Resource information | Optional resource intelligence. |
| Resource Assignments | Resources assigned to activities | Optional workforce/equipment analysis. |
| Expenses | Expense-related activity information | Optional cost impact analysis. |

# 19. API-Based Export and Integration

If the organization uses Primavera Cloud/P6 environments with API access, the integration can be automated rather than relying on a person to manually upload a file.

Oracle's current Primavera Cloud REST API documents endpoints to export P6 XER and P6 XML. The export operation creates a background job; the integration can check job status and then download the resulting XML/XER file.

SiteSync Backend
      │
      │ REST API request
      ▼
Primavera Cloud
      │
      │ Export job
      ▼
XER / XML file
      │
      │ Download
      ▼
SiteSync Importer

## 19.1 Current Primavera Cloud REST API flow

1. Authenticate with the appropriate Primavera Cloud/API credentials and permissions.

2. Call the P6 XER or P6 XML export endpoint with the required workspace/project information.

3. Receive a job identifier.

4. Poll/check the job status until the export job completes.

5. Download the generated XML/XER using the job identifier.

6. Parse and validate the file.

7. Map the imported project/WBS/activity/relationship objects into SiteSync's internal model.

Oracle documents the current REST paths as /api/restapi/action/exportP6xer and /api/restapi/action/exportP6xml, with /api/restapi/action/jobStatus/{jobId} for job status and /api/restapi/action/download/job/{jobId} for downloading the resulting file.

This API route should only be implemented if the team has access to the required Primavera environment, credentials and permissions. For an SIH prototype, manual XER/XML upload is usually much easier to demonstrate reliably.

# 20. Scheduled / Automated Export

P6 Professional documentation states that, when connected to a P6 Professional database, a job service can be configured to export projects at a specified time. This makes a scheduled file-based integration possible.

Example concept:
00:00 → Primavera export
00:05 → SiteSync detects new XER/XML
00:06 → Parse + validate
00:07 → Update internal schedule
00:08 → Recalculate DAG/CPM
00:09 → Dashboard refreshed

The times above are only an architectural example, not a guaranteed execution time.

# 21. What Should SiteSync Extract from Primavera?

For the SIH use case, do not attempt to ingest every Primavera object on day one. Start with the minimum schedule information required to connect field updates to planned activities.

## 21.1 Minimum viable import

| Priority | Data | Reason |
| --- | --- | --- |
| P0 | Project ID / Project Name | Identify the schedule. |
| P0 | WBS Code / WBS Name / Parent WBS | Preserve project hierarchy. |
| P0 | Activity ID / Activity Name | Map field reports to activities. |
| P0 | Activity Start / Finish / Duration | Plan-vs-actual comparison. |
| P0 | Predecessor / Successor | Construct DAG. |
| P0 | Relationship Type | Preserve scheduling logic. |
| P0 | Lag | Preserve dependency timing. |
| P1 | Baseline dates | Measure variance against approved plan. |
| P1 | Calendar | Interpret working time correctly. |
| P1 | Activity status/progress | Initialize current state. |
| P2 | Resources / assignments | Resource-aware impact analysis. |
| P2 | Costs | Cost-impact reporting. |

## 21.2 Recommended internal SiteSync activity object

{
  "project_id": "PIPE-001",
  "wbs_code": "1.2.3.4",
  "wbs_name": "Pipeline Welding",
  "activity_id": "WELD-1042",
  "activity_name": "Weld Joint 1042",
  "planned_start": "2026-09-10",
  "planned_finish": "2026-09-11",
  "duration": 2,
  "percent_complete": 60,
  "predecessors": ["STR-1042"],
  "successors": ["NDT-1042"]
}

The JSON above is a proposed SiteSync internal representation, not an Oracle-defined schema.

# 22. Mapping Primavera Data to the SiteSync Architecture

| Primavera concept | SiteSync concept | Use |
| --- | --- | --- |
| Project | Project | Top-level project identity. |
| WBS hierarchy | Project hierarchy | Context and roll-up. |
| Activity | DAG node / scheduled task | Unit of work. |
| Predecessor / Successor | DAG edge | Dependency logic. |
| Relationship Type | Edge type | FS/SS/FF/SF logic. |
| Lag | Edge timing constraint | Delay/lead between activities. |
| Baseline | Baseline plan | Stable reference for variance. |
| Current dates | Current planned schedule | Latest schedule state. |
| Actual start/finish/progress | Actual field state | Execution reality. |
| Data Date | Schedule evaluation point | Align schedule calculations with reporting period. |

# 23. How a Field Update Should Map Back to Primavera

Suppose a field worker says: 'Welding at section 24 is 60 percent complete. Equipment maintenance caused a delay.'

Voice input
   ↓
Speech-to-text
   ↓
NLP / structured extraction
   ↓
Identify activity: WELD-024
   ↓
Update actual progress + issue event
   ↓
Store locally if offline
   ↓
CRDT synchronization when online
   ↓
Apply event to SiteSync state
   ↓
Recalculate schedule impact
   ↓
Check downstream activities / critical path
   ↓
Update dashboard

The important design principle is that the natural-language field report must ultimately resolve to a stable scheduled activity identifier. If the system cannot confidently identify the target activity, it should ask for confirmation rather than silently updating the wrong activity.

# 24. Recommended Import Architecture for the SIH Prototype

PRIMAVERA P6
                       │
                 XER / P6 XML
                       │
                       ▼
                ┌──────────────┐
                │ File Upload  │
                └──────┬───────┘
                       ▼
                ┌──────────────┐
                │ Parser       │
                └──────┬───────┘
                       ▼
        ┌──────────────┴──────────────┐
        │                             │
        ▼                             ▼
   WBS / Project                 Activities
                                      │
                                      ▼
                                Relationships
                                      │
                                      ▼
                                     DAG
                                      │
                                      ▼
                                    CPM
                                      │
                                      ▼
                              SiteSync Database
                                      ▲
                                      │
                               Field Updates
                                      │
                              Offline + CRDT

Recommended SIH implementation order:

1. Start with XER or P6 XML file upload.

2. Parse Project + WBS + Activity + Relationship data.

3. Store a normalized internal representation in PostgreSQL.

4. Construct a DAG using Activity IDs as nodes and relationships as edges.

5. Create the worker-facing offline capture interface.

6. Map field reports to Activity IDs.

7. Record field changes as immutable events.

8. Recalculate downstream/critical-path impact after synchronization.

9. Display plan vs actual and risk status on the dashboard.

10. Only after the file-based pipeline works, consider live API integration.

# 25. Important Technical Caveats

## 25.1 Do not hard-code L1–L6 meanings

Different organizations define WBS levels differently. SiteSync should import the actual WBS hierarchy and preserve parent-child relationships instead of assuming fixed semantics for each level.

## 25.2 Do not treat Activity Name as the primary key

Activity names may be duplicated or changed. Activity ID is the stable identifier that should be used for matching wherever possible. Oracle's P6 XML/XER import documentation explicitly identifies Activity ID as the matching field for Activity objects.

## 25.3 Do not flatten all relationships to FS

Primavera supports FS, SS, FF and SF relationships and lag. The graph representation should retain relationship type and lag.

## 25.4 Do not treat every percentage as the same

P6 can calculate Activity % Complete from Duration, Units or Physical completion, and Primavera Cloud has additional scope-related behavior. SiteSync should know which progress metric it is receiving.

## 25.5 Export formats are not equivalent

XER, P6 XML and XLSX do not contain exactly the same information or provide the same fidelity. Oracle explicitly notes that some spreadsheet and Microsoft Project formats do not support the complete set of project information.

## 25.6 Preserve project version / schedule context

If SiteSync imports a schedule, then field events occur over time, the system should record which imported schedule/version they were mapped against. Otherwise it can become difficult to explain why an activity looked different after a later schedule import.

## 25.7 Cross-project relationships need special care

Large enterprise schedules can contain dependencies across projects. Oracle's XER relationship mapping includes predecessor and successor project identifiers. SiteSync should not assume every relationship exists inside one project.

# 26. Frequently Asked Questions for Team Discussion

Q: What is Primavera?

A: A professional project planning and scheduling platform used to model, schedule and monitor complex projects.

Q: What is WBS?

A: Work Breakdown Structure — the hierarchical breakdown used to organize project work.

Q: What are L1–L6?

A: Hierarchy levels within a WBS or project breakdown convention. Their exact meanings are organization-specific, not fixed by Primavera.

Q: What is an activity?

A: A schedulable unit of work or milestone with dates, duration, status/progress and relationships.

Q: What is an Activity ID?

A: A unique identifier for an activity; it is the preferred key for matching imported schedule data to SiteSync updates.

Q: What is a predecessor?

A: An activity that logically constrains another activity.

Q: What is a successor?

A: An activity that is logically dependent on another activity.

Q: What is FS?

A: Finish-to-Start: the successor starts after the predecessor finishes, subject to lag and other schedule rules.

Q: What is XER?

A: Oracle Primavera's proprietary exchange format for P6 project information.

Q: What is P6 XML?

A: A structured XML exchange format for P6 project information.

Q: Can Primavera export Excel?

A: Yes. P6 Professional provides spreadsheet exports for activities, activity relationships, expenses, resources and resource assignments.

Q: Can Primavera export automatically?

A: P6 Professional can support scheduled/job-service export in appropriate connected database environments; Primavera Cloud also provides API-based export jobs.

Q: How does SiteSync use Primavera?

A: It can import the planned schedule, preserve WBS and activity relationships, then attach actual field updates to the correct activity and analyze schedule impact.

Q: Does SiteSync replace Primavera?

A: It should be positioned as a field execution/progress and schedule-linking layer, not as a replacement for an enterprise scheduling system unless the project scope explicitly requires replacement.

Q: Why use a DAG?

A: Activities become nodes and dependency relationships become directed edges, enabling graph-based downstream and critical-path analysis.

# 27. Recommended Team Position for SIH

The strongest and most defensible way to present Primavera in the SiteSync solution is:

Primavera = source of planned project schedule
SiteSync = offline-first actual-progress capture + synchronization + schedule-linking layer
DAG/CPM = impact-analysis engine
Dashboard = management view of plan vs actual and schedule risk

This avoids claiming that SiteSync is replacing Primavera. Instead, it addresses a practical gap: field execution data is difficult to capture quickly and reliably in remote environments, while the enterprise schedule already exists in a structured planning system.

For the SIH prototype, the recommended demonstration is to import a representative Primavera XER/P6 XML schedule, show the WBS and activities, capture an offline worker update, synchronize it, map it to an activity, update the event log, recalculate the dependency graph, and display the resulting plan-vs-actual/critical-path impact.

# 28. Official Sources and Further Reading

The following Oracle sources were used for the research in this document. Product behavior can vary by P6 Professional/P6 EPPM/Primavera Cloud version, so the team should always verify the exact environment used by the target organization.

Oracle — P6 Professional Importing and Exporting Guide: https://docs.oracle.com/cd/F25600_01/English/admin/p6_pro_importing_exporting/p6_pro_importing_exporting.pdf

Oracle — Exporting information using a wizard: https://docs.oracle.com/cd/F88968_01/English/admin/p6_pro_importing_exporting/exporting_information_using_a_wizard.htm

Oracle — Primavera P6 Professional XER export: https://docs.oracle.com/cd/F51303_01/English/admin/p6_pro_importing_exporting/export_projects_to_an_xer_file.htm

Oracle — P6 EPPM XER Import/Export Data Map Guide: https://docs.oracle.com/cd/G18294_01/English/Mapping_and_Schema/xer_import_export_data_map_project/toc.htm

Oracle — TASKPRED Activity Relationships Data Map: https://docs.oracle.com/cd/F74771_01/English/Mapping_and_Schema/xer_import_export_data_map_project/97914.htm

Oracle — Primavera Cloud Import/Export to P6 Overview: https://primavera.oraclecloud.com/help/en/user/95912.htm

Oracle — Export Primavera Cloud data to P6 XML/XER: https://primavera.oraclecloud.com/help/en/user/144609.htm

Oracle — Primavera Cloud P6 Import/Export REST endpoints: https://docs.oracle.com/en/industries/construction-engineering/primavera-cloud/rest-api/api-p6-import-export.html

Oracle — Export P6 XER REST API: https://docs.oracle.com/en/industries/construction-engineering/primavera-cloud/rest-api/op-action-exportp6xer-post.html

Oracle — Export P6 XML REST API: https://docs.oracle.com/en/industries/construction-engineering/primavera-cloud/rest-api/op-action-exportp6xml-post.html

Oracle — Download exported P6 XML/XER: https://docs.oracle.com/en/industries/construction-engineering/primavera-cloud/rest-api/op-action-download-job-jobid-get.html

Oracle — WBS management in Primavera Cloud: https://primavera.oraclecloud.com/help/en/user/256738.htm

Oracle — Activity fields / percent complete: https://docs.oracle.com/en/industries/construction-engineering/intelligence/subject-area-reference-guide/p6-activity-primaveraactivity.html

Oracle — Activity relationships: https://docs.oracle.com/cd/G48897_01/p6help/en/99042.htm

Oracle — Project Data Date: https://docs.oracle.com/cd/G48902_01/client_help/en_US/dates_tab_-_project_details.htm

# 29. One-Page Quick Reference

| Concept | Remember this |
| --- | --- |
| Primavera P6 | Enterprise-grade project planning and scheduling software. |
| EPS | Organizes projects at enterprise level. |
| WBS | Hierarchical breakdown of work inside a project. |
| L1–L6 | WBS hierarchy levels; meanings are organization-specific. |
| Activity | Actual scheduled unit of work/milestone. |
| Activity ID | Stable identifier used to match activities. |
| Relationship | Dependency between activities. |
| FS/SS/FF/SF | Four relationship types. |
| Lag | Positive/negative time offset in a relationship. |
| Data Date | Date used as the starting point for schedule calculation. |
| Baseline | Reference plan used for comparison. |
| XER | Oracle proprietary Primavera exchange format. |
| P6 XML | Structured XML exchange format. |
| XLSX | Spreadsheet export for selected information. |
| CRDT | SiteSync mechanism for offline synchronization. |
| Event Sourcing | SiteSync mechanism for immutable historical events. |
| DAG | SiteSync representation of activities + dependencies. |
| CPM | Critical Path Method used to analyze schedule impact. |