SIH 2026 • SIH26122

# SIH26122 MASTER RESEARCH COMPENDIUM

Research • Prior Art • Datasets • Unique Features • Demo Blueprint

THE ONE-LINE IDEA Build the missing bridge between field reality and the approved project schedule: capture evidence, identify the right Activity ID, verify the update, and explain its downstream impact.

| Already exists | The gap | Our layer |
| --- | --- | --- |
| OIL project/digital systems + structured plans | Field reality is messy, distributed and delayed | Capture + understand + link + verify |
| Primavera/P6-style schedule | A field report rarely arrives as a clean Activity ID update | Activity-ID mapping + confidence |
| Dashboards | A red KPI does not explain cause or evidence | Evidence + dependency impact + audit trail |

This document intentionally separates: (1) what we researched about the problem, (2) what similar research has already done, (3) what data can be reused, and (4) what we can make distinctive.

# 1. What Are We Actually Building?

SIMPLE VERSION The schedule knows what should happen. The field knows what actually happened. Our system connects the two reliably.

| Step | Example | Our job |
| --- | --- | --- |
| 1. Planned | WELD-1042 is scheduled for Section B. | Import the schedule. |
| 2. Reported | “Section B welding: 7.2 km completed; maintenance caused delay.” | Understand the report. |
| 3. Linked | Which Activity ID does this mean? | Find the best Activity ID. |
| 4. Verified | Does the evidence support 7.2 km? | Validate + confidence + human review. |
| 5. Impacted | Does the delay affect NDT, coating or hydrotest? | Run dependency/CPM impact. |
| 6. Explained | Why is the milestone now at risk? | Show the cause-and-effect chain. |

## Why OIL makes this problem interesting

- OIL already has project-management and digital systems; the opportunity is the planning-to-execution bridge, not another generic dashboard.

- Field data can include daily progress, quantities, location/chainage, timestamps, GPS, photos/videos, measurements, inspection evidence and delay/blocker reasons.

- Pipeline work is a strong demo because progress is measurable and dependencies are easy to demonstrate.

The OIL research identifies TIEMCHART, SAP and DRIVE/DRIVE 2.0 as existing context and positions the SIH opportunity as an intelligent data-capture/reconciliation layer. fileciteturn4file0L38-L89

# 2. The Few Primavera Concepts Everyone on the Team Must Know

| Term | Simple meaning | What we use it for |
| --- | --- | --- |
| Project | The overall project. | Identity. |
| WBS | Hierarchy that organizes work. | Context. |
| Activity | One scheduled unit of work/milestone. | The thing we ultimately update. |
| Activity ID | Stable ID such as WELD-1042. | Primary matching key. |
| Predecessor | Activity that logically comes before. | Sequence/context. |
| Successor | Activity that depends on another. | Downstream impact. |
| FS/SS/FF/SF | Types of dependency. | Preserve actual scheduling logic. |
| Lag | Time offset in a dependency. | Accurate impact. |
| Baseline | Approved/reference plan. | Variance. |
| Data Date | Date at which schedule is evaluated. | Correct schedule calculation. |
| Critical Path | Activities controlling project finish. | Priority/risk. |

IMPORTANT L1–L6 are hierarchy levels, not universal Oracle meanings. WBS code/name and Activity ID/name are different things. Do not use Activity Name as the primary key.

# 3. What Data Comes In — and Why It Matters

| Input | Example | Useful information |
| --- | --- | --- |
| Voice/text | “Welding section 24 is 60% complete.” | Activity clues, progress, issue. |
| Forms | Quantity, unit, date, status. | Structured facts. |
| Documents | DPR, spreadsheet, scanned diary. | Project/activity/quantity/date. |
| Photos/videos | Site evidence. | Visual confirmation. |
| Measurement | 7.2 km / 120 welds. | Objective progress. |
| Location | GPS / chainage / section. | Strong matching clue. |
| Procurement | PO, promised delivery, receipt. | Readiness/blocker. |
| QA/HSE | Inspection/test/NCR/permit. | Evidence or blocker. |

## The minimum trustworthy progress record

| Field | Why |
| --- | --- |
| Project + Activity ID | Where this update belongs. |
| Reported time + schedule version | When and against which plan. |
| Quantity + unit | What physically happened. |
| Progress rule | How the percentage was calculated. |
| Location | Where it happened. |
| Evidence | Why we should trust it. |
| Verification | Who/what approved it. |
| Issue/blocker | What caused delay. |
| Event ID/history | What changed and when. |

OIL’s research emphasizes evidence-backed progress rather than a bare percentage. Example: 10 km planned, 7.2 km actual, 72% calculated, supported by photos, measurement, GPS and engineer verification. fileciteturn4file9L754-L769

# 4. How the System Connects a Field Report to the Schedule

CORE FLOW Field input → extract facts → find candidate activities → score candidates → verify → create event → calculate progress → recalculate dependencies → explain impact.

| Matching clue | Example | Role |
| --- | --- | --- |
| Activity ID | WELD-1042 appears directly. | Strongest. |
| Name/semantic meaning | “Weld joint 1042”. | Strong. |
| WBS/context | Pipeline welding, Section B. | Strong. |
| Location | Chainage/section/GPS matches. | Strong. |
| Date | Report date fits activity window. | Supporting. |
| Quantity/unit | km matches activity measure. | Supporting. |
| Dependency context | Welding before NDT. | Validation. |
| Evidence | Measurement/photo/inspection. | Trust/validation. |

HARD RULE If two activities look plausible and confidence is low, ask the supervisor. Never silently update the wrong Activity ID.

# 5. Our Unique Features — The Six We Should Build Around

These are the six features from the earlier research direction. Each is written so a teammate can understand the complete purpose just by reading the box.

## 1. Evidence-Grounded Activity-ID Linking

| What it means | One concrete example | Types | Why it matters |
| --- | --- | --- | --- |
| The system does not decide an Activity ID from text alone. It combines the report’s meaning with location, date, WBS, quantity/unit and evidence, then explains why the chosen activity is the best match. | Example: “7.2 km welding completed in Section B” → candidate WELD-1042 scores highly because it is a welding activity for that section, uses km as the progress unit, falls in the reporting window, and has attached measurement/photo evidence. | Types: exact-ID match • semantic match • WBS/context match • location/chainage match • quantity/unit match • date-window match • evidence-supported match. | Value: turns an ambiguous field statement into an auditable, schedule-linked fact. |

## 2. Dependency-Aware Contextual Matching

| What it means | One concrete example | Types | Why it matters |
| --- | --- | --- | --- |
| The schedule’s dependency graph becomes part of the matching logic. The system checks whether a proposed interpretation makes sense relative to predecessors, successors and work sequence. | Example: a report says NDT is complete, but the candidate welding activity for that work front is only 10% complete. Instead of blindly accepting the update, the system flags a sequence inconsistency for review. | Types: predecessor consistency • successor consistency • work-front sequence • dependency type/lag • cross-project dependency checks. | Value: the schedule is used as intelligence for understanding reality, not just as a list of activities. |

## 3. Uncertainty-Aware Human Verification

| What it means | One concrete example | Types | Why it matters |
| --- | --- | --- | --- |
| AI is allowed to recommend; it is not allowed to hide uncertainty. Every important mapping has a confidence score and a clear decision path. | Example: two activities are both named “Valve Installation.” The system shows the two candidates, the matching clues and confidence, then asks the supervisor to select the correct one. | Types: high-confidence auto-suggest • review-required • mandatory confirmation • needs-more-evidence • rejected/ambiguous. | Value: protects the project from silent AI errors and creates an audit trail for consequential updates. |

## 4. Offline-First Capture + CRDT Synchronization

| What it means | One concrete example | Types | Why it matters |
| --- | --- | --- | --- |
| Field users can record updates even without internet. The device stores events locally and synchronizes when connectivity returns. CRDT-style synchronization helps replicas converge, while business rules still handle conflicting physical-progress claims. | Example: an engineer records 12 welds + three photos in a remote area with no network. Later, the phone reconnects and the events synchronize without requiring the engineer to re-enter them. | Types: local event queue • retry/resume • attachment sync • conflict detection • CRDT-style convergence • human conflict resolution. | Value: remote connectivity stops being a reason for missing or late field data. |

## 5. Explainable Delay Propagation

| What it means | One concrete example | Types | Why it matters |
| --- | --- | --- | --- |
| The system does not stop at “Activity X is late.” It follows the dependency graph and explains which downstream activities, float and milestones may be affected. | Example: equipment delivery +13 days → installation starts late → electrical work shifts → testing window tightens → commissioning milestone becomes at risk. | Types: direct successor impact • float consumption • critical-path impact • milestone risk • blocker chain • cross-project impact. | Value: management gets an actionable cause-and-effect story rather than another red dashboard tile. |

## 6. Execution Memory → Future Planning

| What it means | One concrete example | Types | Why it matters |
| --- | --- | --- | --- |
| Every accepted execution event becomes organizational memory. Over time, historical progress, productivity, blockers and delays can inform future schedules and risk assumptions. | Example: repeated projects show that a particular procurement-to-installation sequence regularly takes longer than planned. The system can surface that historical pattern when a new project is planned. | Types: actual duration history • productivity rates • recurring blockers • contractor patterns • material lead times • repeated delay causes • historical activity performance. | Value: the product becomes smarter over time instead of remaining only a live monitoring tool. |

# 6. Similar Research — What Already Exists?

The important question is not “Has anyone ever done this?” Several pieces already exist. The important question is: “Which pieces exist separately, and what combination is still missing for our OIL use case?”

| Research | What it does | Overlap with us |
| --- | --- | --- |
| Pal et al. (2025/2026) | Automatic mapping of schedule activities and reality models for tracking construction progress | Maps schedule activities to reality-model components using visual data, 3D/BIM and semantic/location information. |
| RealCONs (2026) | A digital monitoring, delay detection and visualisation framework for construction projects | Combines QR/mobile monitoring, BIM, P6, cloud SQL and Power BI; evaluates live project control and delay detection. |
| UniformatBridge (2024) | Transformer language model for mapping construction schedule activities to UniFormat categories | BERT-based schedule classification; explicitly injects predecessor/successor sequence information. |
| ALPMS (2024) | Activity-level construction progress monitoring through semantic segmentation of 3D-informed orthographic images | Uses site imagery, 4D BIM and semantic segmentation to estimate activity completion. |
| DT-SYNC (2022) | Digital twin-enabled real-time synchronization for planning, scheduling, and execution in precast on-site assembly | Synchronizes planning, scheduling and execution using a digital twin and real-time data. |
| Xiao et al. (2024) | Automated daily report generation from construction videos using ChatGPT and computer vision | CV extracts productivity/activity information and an LLM generates daily reports. |
| Pfitzner et al. (2024) | From data to knowledge: Construction process analysis through continuous image capturing, object detection, and knowledge graph creation | Continuous site images → object detection → spatiotemporal knowledge graph → process metrics/bottlenecks. |
| Lin (2023) | Prototyping a Chatbot for Site Managers Using BIM and NLU Techniques | Conversational NLU + BIM for site-manager information retrieval. |

# 7. Side-by-Side Comparison — What They Have vs What We Combine

| Capability | Pal | RealCONs | Uniformat | ALPMS | DT-SYNC | Our target |
| --- | --- | --- | --- | --- | --- | --- |
| Schedule ↔ reality/activity | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| P6 explicitly involved | — | ✓ | — | — | — | ✓ |
| Heterogeneous field text/voice/docs | Partial | Partial | Text | Visual | Data-driven | ✓ |
| Evidence-grounded Activity ID | Partial | Partial | No | No | Partial | ✓ |
| Dependency-aware matching | Partial | ✓ | ✓ sequence | 4D | ✓ | ✓ |
| Confidence + human gate | Not central | Not central | Model confidence | Not central | Not central | ✓ |
| Offline-first field capture | — | Mobile | — | — | — | ✓ |
| Immutable execution history | — | Not central | — | — | — | ✓ |
| Explainable delay propagation | Partial | ✓ | — | — | ✓ | ✓ |
| Future planning memory | Partial | Partial | — | — | ✓ | ✓ |
| OIL integration posture | — | — | — | — | — | ✓ |

OUR DEFENSIBLE DIFFERENTIATOR Not “we invented schedule linking.” Our differentiation is the unified, evidence-grounded, uncertainty-aware, dependency-aware execution-to-schedule layer designed to work with messy field inputs, weak connectivity, audit requirements and existing OIL systems.

# 8. Datasets — What Can We Actually Reuse?

IMPORTANT There is no single Kaggle-style dataset that exactly matches SIH26122. The papers below use project-specific or research datasets. I checked for public reuse links; where none was found, the table says so rather than inventing a download link.

| Project | What dataset/data was used | Public availability found | How useful to us |
| --- | --- | --- | --- |
| UniformatBridge | 35,998 manually labeled activity sequence tuples from 10 commercial building projects. | Dataset is described in the paper/dissertation; I did not find a verified public download repository. | Use the paper’s dataset description to build a smaller synthetic/representative schedule-linking set. |
| ALPMS | Semantic segmentation dataset for activity-level progress monitoring; validated across two building projects and ~500 BIM elements. | Paper confirms the dataset exists, but no verified direct public download link was located in this search. | Good conceptual source for CV/segmentation, but not a direct plug-in dataset unless authors provide access. |
| RealCONs | 90-day project monitoring study; supplementary files include codes and an Earned Schedule dataset. Main project data is confidential. | Supplementary files are downloadable from the paper page; main data is confidential. | Best directly reusable piece from the P6/delay-monitoring literature. |
| Pfitzner et al. | 2.1M crane-camera images across four construction sites; additional data fused into a knowledge graph. | Authors state parts of the data can be made available on request; no open bulk download found. | Excellent reference for designing execution-memory/knowledge-graph concepts, not a ready Kaggle dataset. |
| JULIE chatbot | Small public NLU dataset: construction site-manager intents, utterances and labeled entities. | Public GitHub repository is available. | Immediately reusable for testing voice/text intent/entity extraction patterns. |
| Automated daily reports | One-month real construction-site video study in Hong Kong. | No verified public project-video download found; case data appears research-specific. | Use the paper for architecture and evaluation ideas; do not assume the videos are public. |
| DT-SYNC | Precast on-site assembly case data supporting real-time planning/scheduling/execution synchronization. | No verified public dataset download found. | Use for system/process design, not as a drop-in dataset. |

## Direct dataset / supplementary links

JULIE public GitHub dataset/repository: JULIE public GitHub dataset/repository

RealCONs paper + supplementary files: RealCONs paper + supplementary files

ALPMS paper — dataset description: ALPMS paper — dataset description

UniformatBridge paper — dataset description: UniformatBridge paper — dataset description

Pfitzner paper — data availability / request route: Pfitzner paper — data availability / request route

Dataset availability is a major constraint: RealCONs explicitly says its main data is confidential despite supplementary files; Pfitzner et al. says parts of its data can be made available on request. citeturn0search3turn0search0

# 9. Google Scholar Links — One Working Search per Research Project

These are deliberately Google Scholar search links targeted to the exact paper title. They are safer for the team than relying on a fragile direct-result URL.

Pal — Automatic mapping of schedule activities and reality models: Pal — Automatic mapping of schedule activities and reality models

RealCONs — digital monitoring, delay detection and visualisation: RealCONs — digital monitoring, delay detection and visualisation

UniformatBridge — transformer schedule activity mapping: UniformatBridge — transformer schedule activity mapping

ALPMS — activity-level construction progress monitoring: ALPMS — activity-level construction progress monitoring

DT-SYNC — digital twin real-time synchronization: DT-SYNC — digital twin real-time synchronization

Xiao et al. — automated daily report generation: Xiao et al. — automated daily report generation

Pfitzner et al. — construction process knowledge graph: Pfitzner et al. — construction process knowledge graph

Lin — site manager chatbot: Lin — site manager chatbot

## Direct paper links for cross-checking

Pal 2025/26: Pal 2025/26

RealCONs 2026: RealCONs 2026

UniformatBridge 2024: UniformatBridge 2024

ALPMS 2024: ALPMS 2024

DT-SYNC 2022: DT-SYNC 2022

Daily report generation 2024: Daily report generation 2024

Pfitzner 2024: Pfitzner 2024

JULIE 2023: JULIE 2023

# 10. Recommended Demo — Pipeline Rehabilitation

| Demo step | What the judge sees | Feature demonstrated |
| --- | --- | --- |
| 1. Import plan | XER/XML/XLSX → Project/WBS/Activities/relationships. | P6 bridge. |
| 2. Give messy input | Voice: “Section B welding is 72%; 7.2 km measured; maintenance delayed us.” | Intelligent capture. |
| 3. Show match | WELD-1042 selected with reasons + confidence. | Evidence-grounded linking. |
| 4. Show evidence | Photo + measurement + GPS + verification. | Trust. |
| 5. Go offline | Record another update without network. | Offline-first. |
| 6. Sync | Reconnect → event arrives and converges. | Synchronization. |
| 7. Trigger delay | Equipment/procurement delay affects successors. | Dependency intelligence. |
| 8. Explain risk | NDT/coating/lowering/hydrotest and milestone impact. | Explainable propagation. |
| 9. Open history | See every accepted update/correction. | Execution memory. |

THE BEST JUDGE QUESTION TO DESIGN FOR “Why did your system map this report to WELD-1042?” → Show semantic meaning + location + date + quantity/unit + dependency consistency + evidence + confidence. This makes the system explainable rather than merely AI-generated.

# 11. Build Order — Do Not Start With Fancy AI

| Order | Build | Reason |
| --- | --- | --- |
| 1 | Representative P6 schedule import | You need the target activities before linking field data. |
| 2 | Canonical Project/WBS/Activity model | Stable foundation. |
| 3 | Activity matching engine | This is the core problem. |
| 4 | Evidence + confidence gate | Make the mapping trustworthy. |
| 5 | Offline field capture + event sync | Make field data reliable. |
| 6 | DAG + CPM impact | Turn updates into schedule intelligence. |
| 7 | Dashboard/explanations | Make the result understandable. |
| 8 | OCR/NLP/CV/forecasting | Add automation after the core works. |

## Do not overclaim

- Do not claim direct SAP/TIEMCHART integration without an actual interface/specification.

- Do not silently let AI approve consequential progress.

- Do not treat every percentage as the same kind of progress.

- Do not hard-code L1–L6 meanings.

- Do not flatten FS/SS/FF/SF relationships into only FS.

- Do not use Activity Name as the primary key.

# 12. Final Team Mental Model

| Layer | Remember it as |
| --- | --- |
| PLAN | Primavera / approved schedule = what should happen. |
| REALITY | Field evidence = what actually happened. |
| LINK | Activity ID = where the reality belongs. |
| TRUST | Evidence + confidence + human verification = why we believe it. |
| SYNC | Offline events = reality is captured even without connectivity. |
| IMPACT | DAG/CPM = what the change does to the rest of the schedule. |
| MEMORY | Immutable events = what happened is never silently lost. |
| LEARNING | Historical execution = future planning becomes better. |

30-SECOND PITCH OIL already has project systems and planned schedules. The missing bridge is reliable execution reality. We capture field evidence from voice, forms, documents and measurements; identify the correct Activity ID using context and dependencies; validate it with evidence and confidence; work offline; preserve the event history; and explain downstream schedule impact. We are not replacing Primavera or OIL’s systems — we are making the field-to-plan connection intelligent and trustworthy.

Source basis: OIL research and Primavera research supplied by the team, plus the prior-art and dataset verification summarized above. The OIL research explicitly frames the solution as a reliable intelligence layer rather than a replacement project-management system. fileciteturn4file6L459-L466